## Sheet1
MONTH	September			January
WEEK (dd-dd)	Week 0 (19th - 25th )	Week 1 (26th- Oct 02)		Week 14(26th – Jan 1st)	Week 15 (2nd - 8th)	Week 16 (9th - 15th)	Week 17 (16th – 22nd )
Activity(ies)	Welcome week lectures	Draw up initial informal report		Review versioning	Start beefing up review	Exams period
	Establish contact	Meeting of Friday
		Submission of plan		Exam preparation Exam preparation

October				February
Week 2 (3rd - 9th )	Week 3 (10th - 16th )	Week 4 (17th - 23rd )	Week 5 (24th - 30th )	Week 18 (23rd - 29th)	Week 19 (Jan 30th - 05th )	Week 20 (06th – 12th )	Week 21 (13th - 19th )	Week 22 (20th - 26th )
Continue looking at technologies	Start intro in report	Finalise definition	Start considering seminar	Exams period	Start of school	Polish and UI		Fix bugs
Update inf. Report / logbook	Start the definition	Maybe Finalise Nature	Make sure all intro topics are built to code		Recap everything that has been going on	Review and start looking at	Start implementing tests	Prep presentation
Maybe even start report template	And also the nature	Start Alternatives, weave	Choose path for first iteration		Decide if there is time for a third part	methods of testing
					Or work on comparing results
November
Week 6 (Reading week)	Week 7 (07th - 13th )	Week 8 (14th - 20th )	Week 9 ( 21st - 27th )	March
Do some reading	Have Seminar			Week 23 (27th - 3rd )	Week 24 (6th - 12th )	Week 25 (13th - 19th )	Week 26 (20th - 26th )
Literally?	Middle code	Towards End code	Start second iteration	Fix bugs	Presentation of Results Period
Have seminar fleshed out	Update report	Finalise the first iteration	Bring documentation up to scratch	Prep presentation			24th – Practical work stops	27th – Code submission
Code, please code	NOV 8th	Go over options	See if there is a third option

December
Week 10 (Nov 28th - 4th )	Week 11 ( 05th - 11th )	Week 12 (12th - 18th )	Week 13 (19th - 25th)
Have Seminar	Review Seminar	Start polishing report	Holiday? Holiday Holiday Holiday
Middle code	Review choices	Determine sections	Exam preparation
Implement second iteration	Start ending code	Finish Second iteration