## Sheet1
MONTH	September		October				November				December				January				February					March
WEEK (dd-dd)	Week 0 (19th - 25th )	Week 1 (26th- Oct 02)	Week 2 (3rd - 9th )	Week 3 (10th - 16th )	Week 4 (17th - 23rd )	Week 5 (24th - 30th )	Week 6 (Reading week)	Week 7 (07th - 13th )	Week 8 (14th - 20th )	Week 9 ( 21st - 27th )	Week 10	Week 11	Week 12	Holiday? Holiday Holiday Holiday				Week 17	Week 18	Week 19 (Jan 30th - 05th )	Week 20 (Feb 06th – Feb 12th )	Week 21 (13th - 19th )	Week 22 (20th - 26th )	Week 23 (Feb 27th - 3rd )	Week 24 (6th - 12th )	Week 25 (13th - 19th )	Week 26 (20th - 26th )
Activity(ies)	Welcome week lectures	Draw up initial informal report	Continue looking at technologies	Start intro in report	Finalise definition	Start considering seminar	Do some reading	Have Seminar				Review Seminar	Start polishing report		Review versioning		Exams period			Start of school	Polish and UI		Fix bugs		Presentation of Results Period
	Establish contact	Meeting of Friday	Update inf. Report / logbook	Start the definition	Maybe Finalise Nature	Make sure all intro topics are built to code	Literally?	Middle code	Towards End code	Start second iteration	Middle code	Review choices	Determine sections		Start beefing up review					Recap everything that has been going on	Review and start looking at	Start implementing tests					24th – Practical work stops	27th – Code submission
		Submission of plan	Maybe even start report template	And also the nature	Start Alternatives, weave	Choose path for first iteration	Have seminar fleshed out	Update report	Finalise the first iteration	Bring documentation up to scratch	Implement second iteration	Start ending code	Finish Second iteration	Exam preparation						Decide if there is time for a third part, or comparative	methods of testing
							Code, please code	NOV 8th	Go over options	See if there is a third option